## 1. Projectrollen (2)
Vul je cruciale projectrollen in
Projectrol | SPOF Risico (1-5) | Mitigatie Actie
Software Architect | 5 | Kennisoverdracht!
Project Lead | 2 | OK
Product Owner | 4 | Back-up trainen
Data Scientist | 2 | OK
Business Analist | 4 | Extra capaciteit nodig
DevOps Engineer | 5 | Kritiek risico!

## Algemeen
SPOF analyse voor projectwerking
1. Vul je cruciale projectrollen in
2. Link je medewerkers aan de projectrol en geef hun beschikbaarheden in
3. Geef je projecten in
4. Geef je vraag voor de projecten per rol in
5. Consulteer het dashboard en mitigeer je risico's

## 1. Projectrollen
Vul je cruciale projectrollen in
Projectrol | SPOF Risico (1-5) | Mitigatie Actie
Software Architect | 5 | Kennisoverdracht!
Project Lead | 2 | OK
Product Owner | 4 | Back-up trainen
Data Scientist | 2 | OK
Business Analist | 4 | Extra capaciteit nodig
DevOps Engineer | 5 | Kritiek risico!

## 2. Medewerkers
Vul je medewerkers, risico, rol en hun beschikbaarheid in
Beschikbaarheid voor projectwerk
Naam | SPOF Risico (1-5) | Mitigatie Actie | Rol | apr/26 | mei/26 | jun/26 | jul/26 | aug/26 | sep/26 | okt/26 | nov/26 | dec/26 | jan/27 | feb/27 | mrt/27
Jan De Smet | 5 | Kennisoverdracht! | Software Architect | 0.3 | 0.5 | 0.6 | 1 | 0 | 0 | 0.4 | 0.5 | 0.6 | 0.7 | 0.8 | 0.9
An Verstraete | 2 | OK | Product Owner | 0.4 | 0.4 | 0.4 | 1 | 0.6 | 0.4 | 0.4 | 0.4 | 0.6 | 0.4 | 0.4 | 0.4
Sarah Willems | 4 | Back-up trainen | Project Lead | 0.6 | 0.6 | 0.6 | 0.8 | 0.7 | 0.6 | 0.6 | 0.6 | 0.3 | 0.6 | 0.6 | 0.6
Koen Mertens | 2 | OK | DevOps Engineer | 0.3 | 0.3 | 0.3 | 0.6 | 0.5 | 0.3 | 0.3 | 0.3 | 0.6 | 0.3 | 0.3 | 0.3
Sofie Peeters | 4 | Extra capaciteit nodig | Business Analist | 0.9 | 0.9 | 0.9 | 0.7 | 0.6 | 0.9 | 0.9 | 0.9 | 0.4 | 0.9 | 0.9 | 0.9
Tom Peeters | 5 | Kritiek risico! | Project Lead | 0.8 | 0.8 | 0.8 | 0.5 | 0.4 | 0.8 | 0.8 | 0.8 | 0.5 | 0.8 | 0.8 | 0.8
Sam Pieters | 3 | Monitoren | Software Architect | 0.7 | 0.7 | 0.7 | 0.6 | 0.6 | 0.7 | 0.7 | 0.7 | 0.3 | 0.7 | 0.7 | 0.7

## 3. Project
Vul je projecten, status en hun prioritering in
Projectnaam | Status | Prio
App Development | Ongoing | Must do
Digital Transformation 2.0 | Backlog | Should do
ERP Migratie | Ongoing | Could do
Management dashboard implementatie | Backlog | Should do
NIS2 conformiteit | Ongoing | Must do
Procesoptimalisatie aankoop | Backlog | Could do
Rebranding | On hold | Won't do now

## 4. Project demand
Vul je projectnoden per rol aan
Projectnaam | Rol | apr/26 | mei/26 | jun/26 | jul/26 | aug/26 | sep/26 | okt/26 | nov/26 | dec/26 | jan/27 | feb/27 | mrt/27
Digital Transformation 2.0 | Project Lead | 0.4 | 0.4 | 0.2 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.2 | 0.4 | 0.4 | 0.4
Digital Transformation 2.0 | Product Owner | 0.4 | 0.4 | 0.3 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.3 | 0.4 | 0.4 | 0.4
Digital Transformation 2.0 | Data Scientist | 0 | 0 | 0.2 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.2 | 0.3 | 0.3 | 0.3
Digital Transformation 2.0 | Business Analist | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4
Digital Transformation 2.0 | DevOps Engineer | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
ERP Migratie | Project Lead | 0.7 | 0.7 | 0.7 | 0.4 | 0.4 | 0.4 | 0.3 | 0.2 | 0.5 | 0.3 | 0.3 | 0.3
ERP Migratie | Product Owner | 0.3 | 0.3 | 0.2 | 0.3 | 0.7 | 0.3 | 0.2 | 0.5 | 0.3 | 0.3 | 0.3 | 0.4
ERP Migratie | Data Scientist | 0.3 | 0.5 | 0.4 | 1 | 0 | 0 | 0.4 | 0.5 | 0.2 | 0.7 | 0.5 | 0.4
ERP Migratie | Business Analist | 0.4 | 0.4 | 0.4 | 1 | 0.2 | 0.4 | 0.4 | 0.4 | 0.2 | 0.4 | 0.4 | 0.4
ERP Migratie | DevOps Engineer | 0.4 | 0.4 | 0.4 | 0.5 | 0.1 | 0.4 | 0.4 | 0.4 | 0.3 | 0.4 | 0.4 | 0.4
Management dashboard implementatie | Project Lead | 0.4 | 0.4 | 0.4 | 0.1 | 0.2 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4
Management dashboard implementatie | Product Owner | 0.5 | 0.5 | 0.5 | 0.5 | 0.4 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Management dashboard implementatie | Data Scientist | 0.7 | 0.7 | 0.7 | 0.2 | 0.2 | 0.7 | 0.7 | 0.7 | 0.3 | 0.7 | 0.7 | 0.7
Management dashboard implementatie | Business Analist | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4
Management dashboard implementatie | DevOps Engineer | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
NIS2 conformiteit | Software Architect | 0.7 | 0.7 | 0.3 | 0.7 | 0.7 | 0.7 | 0.7 | 0.7 | 0.3 | 0.7 | 0.7 | 0.7
NIS2 conformiteit | Project Lead | 0.7 | 0.7 | 0.7 | 0.4 | 0.4 | 0.4 | 0.3 | 0.2 | 0.5 | 0.3 | 0.3 | 0.3
NIS2 conformiteit | Product Owner | 0.3 | 0.3 | 0.2 | 0.3 | 0.7 | 0.3 | 0.2 | 0.5 | 0.3 | 0.3 | 0.3 | 0.4
NIS2 conformiteit | Data Scientist | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4
NIS2 conformiteit | Business Analist | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Procesoptimalisatie aankoop | Project Lead | 0.3 | 0.3 | 0.2 | 0.3 | 0.7 | 0.3 | 0.2 | 0.5 | 0.3 | 0.3 | 0.3 | 0.4
Procesoptimalisatie aankoop | Product Owner | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4
Procesoptimalisatie aankoop | Data Scientist | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Procesoptimalisatie aankoop | Business Analist | 0.7 | 0.7 | 0.3 | 0.7 | 0.7 | 0.7 | 0.7 | 0.7 | 0.3 | 0.7 | 0.7 | 0.7
Procesoptimalisatie aankoop | DevOps Engineer | 0.7 | 0.7 | 0.7 | 0.4 | 0.4 | 0.4 | 0.3 | 0.2 | 0.5 | 0.3 | 0.3 | 0.3

## Masterdata (hidden)
Projectnaam | Rol | Maand | FTE | Type | Naam | SPOF Risico (1-5) | Mitigatie Actie | Project.Status
Digital Transformation 2.0 | Project Lead | apr/26 | 0.4 | Demand |  |  |  | Backlog
Digital Transformation 2.0 | Project Lead | mei/26 | 0.4 | Demand |  |  |  | Backlog
Digital Transformation 2.0 | Project Lead | jun/26 | 0.2 | Demand |  |  |  | Backlog
Digital Transformation 2.0 | Project Lead | jul/26 | 0.4 | Demand |  |  |  | Backlog
Digital Transformation 2.0 | Project Lead | aug/26 | 0.4 | Demand |  |  |  | Backlog
Digital Transformation 2.0 | Project Lead | sep/26 | 0.4 | Demand |  |  |  | Backlog
Digital Transformation 2.0 | Project Lead | okt/26 | 0.4 | Demand |  |  |  | Backlog
Digital Transformation 2.0 | Project Lead | nov/26 | 0.4 | Demand |  |  |  | Backlog
Digital Transformation 2.0 | Project Lead | dec/26 | 0.2 | Demand |  |  |  | Backlog
Digital Transformation 2.0 | Project Lead | jan/27 | 0.4 | Demand |  |  |  | Backlog
Digital Transformation 2.0 | Project Lead | feb/27 | 0.4 | Demand |  |  |  | Backlog
Digital Transformation 2.0 | Project Lead | mrt/27 | 0.4 | Demand |  |  |  | Backlog
Digital Transformation 2.0 | Product Owner | apr/26 | 0.4 | Demand |  |  |  | Backlog
Digital Transformation 2.0 | Product Owner | mei/26 | 0.4 | Demand |  |  |  | Backlog
Digital Transformation 2.0 | Product Owner | jun/26 | 0.3 | Demand |  |  |  | Backlog
Digital Transformation 2.0 | Product Owner | jul/26 | 0.4 | Demand |  |  |  | Backlog
Digital Transformation 2.0 | Product Owner | aug/26 | 0.4 | Demand |  |  |  | Backlog
Digital Transformation 2.0 | Product Owner | sep/26 | 0.4 | Demand |  |  |  | Backlog
Digital Transformation 2.0 | Product Owner | okt/26 | 0.4 | Demand |  |  |  | Backlog
Digital Transformation 2.0 | Product Owner | nov/26 | 0.4 | Demand |  |  |  | Backlog
Digital Transformation 2.0 | Product Owner | dec/26 | 0.3 | Demand |  |  |  | Backlog
Digital Transformation 2.0 | Product Owner | jan/27 | 0.4 | Demand |  |  |  | Backlog
Digital Transformation 2.0 | Product Owner | feb/27 | 0.4 | Demand |  |  |  | Backlog
Digital Transformation 2.0 | Product Owner | mrt/27 | 0.4 | Demand |  |  |  | Backlog
Digital Transformation 2.0 | Data Scientist | apr/26 | 0 | Demand |  |  |  | Backlog
Digital Transformation 2.0 | Data Scientist | mei/26 | 0 | Demand |  |  |  | Backlog
Digital Transformation 2.0 | Data Scientist | jun/26 | 0.2 | Demand |  |  |  | Backlog
Digital Transformation 2.0 | Data Scientist | jul/26 | 0.3 | Demand |  |  |  | Backlog
Digital Transformation 2.0 | Data Scientist | aug/26 | 0.3 | Demand |  |  |  | Backlog
Digital Transformation 2.0 | Data Scientist | sep/26 | 0.3 | Demand |  |  |  | Backlog
Digital Transformation 2.0 | Data Scientist | okt/26 | 0.3 | Demand |  |  |  | Backlog
Digital Transformation 2.0 | Data Scientist | nov/26 | 0.3 | Demand |  |  |  | Backlog
Digital Transformation 2.0 | Data Scientist | dec/26 | 0.2 | Demand |  |  |  | Backlog
Digital Transformation 2.0 | Data Scientist | jan/27 | 0.3 | Demand |  |  |  | Backlog
Digital Transformation 2.0 | Data Scientist | feb/27 | 0.3 | Demand |  |  |  | Backlog
Digital Transformation 2.0 | Data Scientist | mrt/27 | 0.3 | Demand |  |  |  | Backlog
Digital Transformation 2.0 | Business Analist | apr/26 | 0.4 | Demand |  |  |  | Backlog
Digital Transformation 2.0 | Business Analist | mei/26 | 0.4 | Demand |  |  |  | Backlog
Digital Transformation 2.0 | Business Analist | jun/26 | 0.4 | Demand |  |  |  | Backlog
Digital Transformation 2.0 | Business Analist | jul/26 | 0.4 | Demand |  |  |  | Backlog
Digital Transformation 2.0 | Business Analist | aug/26 | 0.4 | Demand |  |  |  | Backlog
Digital Transformation 2.0 | Business Analist | sep/26 | 0.4 | Demand |  |  |  | Backlog
Digital Transformation 2.0 | Business Analist | okt/26 | 0.4 | Demand |  |  |  | Backlog
Digital Transformation 2.0 | Business Analist | nov/26 | 0.4 | Demand |  |  |  | Backlog
Digital Transformation 2.0 | Business Analist | dec/26 | 0.4 | Demand |  |  |  | Backlog
Digital Transformation 2.0 | Business Analist | jan/27 | 0.4 | Demand |  |  |  | Backlog
Digital Transformation 2.0 | Business Analist | feb/27 | 0.4 | Demand |  |  |  | Backlog
Digital Transformation 2.0 | Business Analist | mrt/27 | 0.4 | Demand |  |  |  | Backlog
Digital Transformation 2.0 | DevOps Engineer | apr/26 | 0.5 | Demand |  |  |  | Backlog
Digital Transformation 2.0 | DevOps Engineer | mei/26 | 0.5 | Demand |  |  |  | Backlog
Digital Transformation 2.0 | DevOps Engineer | jun/26 | 0.5 | Demand |  |  |  | Backlog
Digital Transformation 2.0 | DevOps Engineer | jul/26 | 0.5 | Demand |  |  |  | Backlog
Digital Transformation 2.0 | DevOps Engineer | aug/26 | 0.5 | Demand |  |  |  | Backlog
Digital Transformation 2.0 | DevOps Engineer | sep/26 | 0.5 | Demand |  |  |  | Backlog
Digital Transformation 2.0 | DevOps Engineer | okt/26 | 0.5 | Demand |  |  |  | Backlog
Digital Transformation 2.0 | DevOps Engineer | nov/26 | 0.5 | Demand |  |  |  | Backlog
Digital Transformation 2.0 | DevOps Engineer | dec/26 | 0.5 | Demand |  |  |  | Backlog
Digital Transformation 2.0 | DevOps Engineer | jan/27 | 0.5 | Demand |  |  |  | Backlog
Digital Transformation 2.0 | DevOps Engineer | feb/27 | 0.5 | Demand |  |  |  | Backlog
Digital Transformation 2.0 | DevOps Engineer | mrt/27 | 0.5 | Demand |  |  |  | Backlog
ERP Migratie | Project Lead | apr/26 | 0.7 | Demand |  |  |  | Ongoing
ERP Migratie | Project Lead | mei/26 | 0.7 | Demand |  |  |  | Ongoing
ERP Migratie | Project Lead | jun/26 | 0.7 | Demand |  |  |  | Ongoing
ERP Migratie | Project Lead | jul/26 | 0.4 | Demand |  |  |  | Ongoing
ERP Migratie | Project Lead | aug/26 | 0.4 | Demand |  |  |  | Ongoing
ERP Migratie | Project Lead | sep/26 | 0.4 | Demand |  |  |  | Ongoing
ERP Migratie | Project Lead | okt/26 | 0.3 | Demand |  |  |  | Ongoing
ERP Migratie | Project Lead | nov/26 | 0.2 | Demand |  |  |  | Ongoing
ERP Migratie | Project Lead | dec/26 | 0.5 | Demand |  |  |  | Ongoing
ERP Migratie | Project Lead | jan/27 | 0.3 | Demand |  |  |  | Ongoing
ERP Migratie | Project Lead | feb/27 | 0.3 | Demand |  |  |  | Ongoing
ERP Migratie | Project Lead | mrt/27 | 0.3 | Demand |  |  |  | Ongoing
ERP Migratie | Product Owner | apr/26 | 0.3 | Demand |  |  |  | Ongoing
ERP Migratie | Product Owner | mei/26 | 0.3 | Demand |  |  |  | Ongoing
ERP Migratie | Product Owner | jun/26 | 0.2 | Demand |  |  |  | Ongoing
ERP Migratie | Product Owner | jul/26 | 0.3 | Demand |  |  |  | Ongoing
ERP Migratie | Product Owner | aug/26 | 0.7 | Demand |  |  |  | Ongoing
ERP Migratie | Product Owner | sep/26 | 0.3 | Demand |  |  |  | Ongoing
ERP Migratie | Product Owner | okt/26 | 0.2 | Demand |  |  |  | Ongoing
ERP Migratie | Product Owner | nov/26 | 0.5 | Demand |  |  |  | Ongoing
ERP Migratie | Product Owner | dec/26 | 0.3 | Demand |  |  |  | Ongoing
ERP Migratie | Product Owner | jan/27 | 0.3 | Demand |  |  |  | Ongoing
ERP Migratie | Product Owner | feb/27 | 0.3 | Demand |  |  |  | Ongoing
ERP Migratie | Product Owner | mrt/27 | 0.4 | Demand |  |  |  | Ongoing
ERP Migratie | Data Scientist | apr/26 | 0.3 | Demand |  |  |  | Ongoing
ERP Migratie | Data Scientist | mei/26 | 0.5 | Demand |  |  |  | Ongoing
ERP Migratie | Data Scientist | jun/26 | 0.4 | Demand |  |  |  | Ongoing
ERP Migratie | Data Scientist | jul/26 | 1 | Demand |  |  |  | Ongoing
ERP Migratie | Data Scientist | aug/26 | 0 | Demand |  |  |  | Ongoing
ERP Migratie | Data Scientist | sep/26 | 0 | Demand |  |  |  | Ongoing
ERP Migratie | Data Scientist | okt/26 | 0.4 | Demand |  |  |  | Ongoing
ERP Migratie | Data Scientist | nov/26 | 0.5 | Demand |  |  |  | Ongoing
ERP Migratie | Data Scientist | dec/26 | 0.2 | Demand |  |  |  | Ongoing
ERP Migratie | Data Scientist | jan/27 | 0.7 | Demand |  |  |  | Ongoing
ERP Migratie | Data Scientist | feb/27 | 0.5 | Demand |  |  |  | Ongoing
ERP Migratie | Data Scientist | mrt/27 | 0.4 | Demand |  |  |  | Ongoing
ERP Migratie | Business Analist | apr/26 | 0.4 | Demand |  |  |  | Ongoing
ERP Migratie | Business Analist | mei/26 | 0.4 | Demand |  |  |  | Ongoing
ERP Migratie | Business Analist | jun/26 | 0.4 | Demand |  |  |  | Ongoing
ERP Migratie | Business Analist | jul/26 | 1 | Demand |  |  |  | Ongoing
ERP Migratie | Business Analist | aug/26 | 0.2 | Demand |  |  |  | Ongoing
ERP Migratie | Business Analist | sep/26 | 0.4 | Demand |  |  |  | Ongoing
ERP Migratie | Business Analist | okt/26 | 0.4 | Demand |  |  |  | Ongoing
ERP Migratie | Business Analist | nov/26 | 0.4 | Demand |  |  |  | Ongoing
ERP Migratie | Business Analist | dec/26 | 0.2 | Demand |  |  |  | Ongoing
ERP Migratie | Business Analist | jan/27 | 0.4 | Demand |  |  |  | Ongoing
ERP Migratie | Business Analist | feb/27 | 0.4 | Demand |  |  |  | Ongoing
ERP Migratie | Business Analist | mrt/27 | 0.4 | Demand |  |  |  | Ongoing
ERP Migratie | DevOps Engineer | apr/26 | 0.4 | Demand |  |  |  | Ongoing
ERP Migratie | DevOps Engineer | mei/26 | 0.4 | Demand |  |  |  | Ongoing
ERP Migratie | DevOps Engineer | jun/26 | 0.4 | Demand |  |  |  | Ongoing
ERP Migratie | DevOps Engineer | jul/26 | 0.5 | Demand |  |  |  | Ongoing
ERP Migratie | DevOps Engineer | aug/26 | 0.1 | Demand |  |  |  | Ongoing
ERP Migratie | DevOps Engineer | sep/26 | 0.4 | Demand |  |  |  | Ongoing
ERP Migratie | DevOps Engineer | okt/26 | 0.4 | Demand |  |  |  | Ongoing
ERP Migratie | DevOps Engineer | nov/26 | 0.4 | Demand |  |  |  | Ongoing
ERP Migratie | DevOps Engineer | dec/26 | 0.3 | Demand |  |  |  | Ongoing
ERP Migratie | DevOps Engineer | jan/27 | 0.4 | Demand |  |  |  | Ongoing
ERP Migratie | DevOps Engineer | feb/27 | 0.4 | Demand |  |  |  | Ongoing
ERP Migratie | DevOps Engineer | mrt/27 | 0.4 | Demand |  |  |  | Ongoing
Management dashboard implementatie | Project Lead | apr/26 | 0.4 | Demand |  |  |  | Backlog
Management dashboard implementatie | Project Lead | mei/26 | 0.4 | Demand |  |  |  | Backlog
Management dashboard implementatie | Project Lead | jun/26 | 0.4 | Demand |  |  |  | Backlog
Management dashboard implementatie | Project Lead | jul/26 | 0.1 | Demand |  |  |  | Backlog
Management dashboard implementatie | Project Lead | aug/26 | 0.2 | Demand |  |  |  | Backlog
Management dashboard implementatie | Project Lead | sep/26 | 0.4 | Demand |  |  |  | Backlog
Management dashboard implementatie | Project Lead | okt/26 | 0.4 | Demand |  |  |  | Backlog
Management dashboard implementatie | Project Lead | nov/26 | 0.4 | Demand |  |  |  | Backlog
Management dashboard implementatie | Project Lead | dec/26 | 0.4 | Demand |  |  |  | Backlog
Management dashboard implementatie | Project Lead | jan/27 | 0.4 | Demand |  |  |  | Backlog
Management dashboard implementatie | Project Lead | feb/27 | 0.4 | Demand |  |  |  | Backlog
Management dashboard implementatie | Project Lead | mrt/27 | 0.4 | Demand |  |  |  | Backlog
Management dashboard implementatie | Product Owner | apr/26 | 0.5 | Demand |  |  |  | Backlog
Management dashboard implementatie | Product Owner | mei/26 | 0.5 | Demand |  |  |  | Backlog
Management dashboard implementatie | Product Owner | jun/26 | 0.5 | Demand |  |  |  | Backlog
Management dashboard implementatie | Product Owner | jul/26 | 0.5 | Demand |  |  |  | Backlog
Management dashboard implementatie | Product Owner | aug/26 | 0.4 | Demand |  |  |  | Backlog
Management dashboard implementatie | Product Owner | sep/26 | 0.5 | Demand |  |  |  | Backlog
Management dashboard implementatie | Product Owner | okt/26 | 0.5 | Demand |  |  |  | Backlog
Management dashboard implementatie | Product Owner | nov/26 | 0.5 | Demand |  |  |  | Backlog
Management dashboard implementatie | Product Owner | dec/26 | 0.5 | Demand |  |  |  | Backlog
Management dashboard implementatie | Product Owner | jan/27 | 0.5 | Demand |  |  |  | Backlog
Management dashboard implementatie | Product Owner | feb/27 | 0.5 | Demand |  |  |  | Backlog
Management dashboard implementatie | Product Owner | mrt/27 | 0.5 | Demand |  |  |  | Backlog
Management dashboard implementatie | Data Scientist | apr/26 | 0.7 | Demand |  |  |  | Backlog
Management dashboard implementatie | Data Scientist | mei/26 | 0.7 | Demand |  |  |  | Backlog
Management dashboard implementatie | Data Scientist | jun/26 | 0.7 | Demand |  |  |  | Backlog
Management dashboard implementatie | Data Scientist | jul/26 | 0.2 | Demand |  |  |  | Backlog
Management dashboard implementatie | Data Scientist | aug/26 | 0.2 | Demand |  |  |  | Backlog
Management dashboard implementatie | Data Scientist | sep/26 | 0.7 | Demand |  |  |  | Backlog
Management dashboard implementatie | Data Scientist | okt/26 | 0.7 | Demand |  |  |  | Backlog
Management dashboard implementatie | Data Scientist | nov/26 | 0.7 | Demand |  |  |  | Backlog
Management dashboard implementatie | Data Scientist | dec/26 | 0.3 | Demand |  |  |  | Backlog
Management dashboard implementatie | Data Scientist | jan/27 | 0.7 | Demand |  |  |  | Backlog
Management dashboard implementatie | Data Scientist | feb/27 | 0.7 | Demand |  |  |  | Backlog
Management dashboard implementatie | Data Scientist | mrt/27 | 0.7 | Demand |  |  |  | Backlog
Management dashboard implementatie | Business Analist | apr/26 | 0.4 | Demand |  |  |  | Backlog
Management dashboard implementatie | Business Analist | mei/26 | 0.4 | Demand |  |  |  | Backlog
Management dashboard implementatie | Business Analist | jun/26 | 0.4 | Demand |  |  |  | Backlog
Management dashboard implementatie | Business Analist | jul/26 | 0.4 | Demand |  |  |  | Backlog
Management dashboard implementatie | Business Analist | aug/26 | 0.4 | Demand |  |  |  | Backlog
Management dashboard implementatie | Business Analist | sep/26 | 0.4 | Demand |  |  |  | Backlog
Management dashboard implementatie | Business Analist | okt/26 | 0.4 | Demand |  |  |  | Backlog
Management dashboard implementatie | Business Analist | nov/26 | 0.4 | Demand |  |  |  | Backlog
Management dashboard implementatie | Business Analist | dec/26 | 0.4 | Demand |  |  |  | Backlog
Management dashboard implementatie | Business Analist | jan/27 | 0.4 | Demand |  |  |  | Backlog
Management dashboard implementatie | Business Analist | feb/27 | 0.4 | Demand |  |  |  | Backlog
Management dashboard implementatie | Business Analist | mrt/27 | 0.4 | Demand |  |  |  | Backlog
Management dashboard implementatie | DevOps Engineer | apr/26 | 0.5 | Demand |  |  |  | Backlog
Management dashboard implementatie | DevOps Engineer | mei/26 | 0.5 | Demand |  |  |  | Backlog
Management dashboard implementatie | DevOps Engineer | jun/26 | 0.5 | Demand |  |  |  | Backlog
Management dashboard implementatie | DevOps Engineer | jul/26 | 0.5 | Demand |  |  |  | Backlog
Management dashboard implementatie | DevOps Engineer | aug/26 | 0.5 | Demand |  |  |  | Backlog
Management dashboard implementatie | DevOps Engineer | sep/26 | 0.5 | Demand |  |  |  | Backlog
Management dashboard implementatie | DevOps Engineer | okt/26 | 0.5 | Demand |  |  |  | Backlog
Management dashboard implementatie | DevOps Engineer | nov/26 | 0.5 | Demand |  |  |  | Backlog
Management dashboard implementatie | DevOps Engineer | dec/26 | 0.5 | Demand |  |  |  | Backlog
Management dashboard implementatie | DevOps Engineer | jan/27 | 0.5 | Demand |  |  |  | Backlog
Management dashboard implementatie | DevOps Engineer | feb/27 | 0.5 | Demand |  |  |  | Backlog
Management dashboard implementatie | DevOps Engineer | mrt/27 | 0.5 | Demand |  |  |  | Backlog
NIS2 conformiteit | Software Architect | apr/26 | 0.7 | Demand |  |  |  | Ongoing
NIS2 conformiteit | Software Architect | mei/26 | 0.7 | Demand |  |  |  | Ongoing
NIS2 conformiteit | Software Architect | jun/26 | 0.3 | Demand |  |  |  | Ongoing
NIS2 conformiteit | Software Architect | jul/26 | 0.7 | Demand |  |  |  | Ongoing
NIS2 conformiteit | Software Architect | aug/26 | 0.7 | Demand |  |  |  | Ongoing
NIS2 conformiteit | Software Architect | sep/26 | 0.7 | Demand |  |  |  | Ongoing
NIS2 conformiteit | Software Architect | okt/26 | 0.7 | Demand |  |  |  | Ongoing
NIS2 conformiteit | Software Architect | nov/26 | 0.7 | Demand |  |  |  | Ongoing
NIS2 conformiteit | Software Architect | dec/26 | 0.3 | Demand |  |  |  | Ongoing
NIS2 conformiteit | Software Architect | jan/27 | 0.7 | Demand |  |  |  | Ongoing
NIS2 conformiteit | Software Architect | feb/27 | 0.7 | Demand |  |  |  | Ongoing
NIS2 conformiteit | Software Architect | mrt/27 | 0.7 | Demand |  |  |  | Ongoing
NIS2 conformiteit | Project Lead | apr/26 | 0.7 | Demand |  |  |  | Ongoing
NIS2 conformiteit | Project Lead | mei/26 | 0.7 | Demand |  |  |  | Ongoing
NIS2 conformiteit | Project Lead | jun/26 | 0.7 | Demand |  |  |  | Ongoing
NIS2 conformiteit | Project Lead | jul/26 | 0.4 | Demand |  |  |  | Ongoing
NIS2 conformiteit | Project Lead | aug/26 | 0.4 | Demand |  |  |  | Ongoing
NIS2 conformiteit | Project Lead | sep/26 | 0.4 | Demand |  |  |  | Ongoing
NIS2 conformiteit | Project Lead | okt/26 | 0.3 | Demand |  |  |  | Ongoing
NIS2 conformiteit | Project Lead | nov/26 | 0.2 | Demand |  |  |  | Ongoing
NIS2 conformiteit | Project Lead | dec/26 | 0.5 | Demand |  |  |  | Ongoing
NIS2 conformiteit | Project Lead | jan/27 | 0.3 | Demand |  |  |  | Ongoing
NIS2 conformiteit | Project Lead | feb/27 | 0.3 | Demand |  |  |  | Ongoing
NIS2 conformiteit | Project Lead | mrt/27 | 0.3 | Demand |  |  |  | Ongoing
NIS2 conformiteit | Product Owner | apr/26 | 0.3 | Demand |  |  |  | Ongoing
NIS2 conformiteit | Product Owner | mei/26 | 0.3 | Demand |  |  |  | Ongoing
NIS2 conformiteit | Product Owner | jun/26 | 0.2 | Demand |  |  |  | Ongoing
NIS2 conformiteit | Product Owner | jul/26 | 0.3 | Demand |  |  |  | Ongoing
NIS2 conformiteit | Product Owner | aug/26 | 0.7 | Demand |  |  |  | Ongoing
NIS2 conformiteit | Product Owner | sep/26 | 0.3 | Demand |  |  |  | Ongoing
NIS2 conformiteit | Product Owner | okt/26 | 0.2 | Demand |  |  |  | Ongoing
NIS2 conformiteit | Product Owner | nov/26 | 0.5 | Demand |  |  |  | Ongoing
NIS2 conformiteit | Product Owner | dec/26 | 0.3 | Demand |  |  |  | Ongoing
NIS2 conformiteit | Product Owner | jan/27 | 0.3 | Demand |  |  |  | Ongoing
NIS2 conformiteit | Product Owner | feb/27 | 0.3 | Demand |  |  |  | Ongoing
NIS2 conformiteit | Product Owner | mrt/27 | 0.4 | Demand |  |  |  | Ongoing
NIS2 conformiteit | Data Scientist | apr/26 | 0.4 | Demand |  |  |  | Ongoing
NIS2 conformiteit | Data Scientist | mei/26 | 0.4 | Demand |  |  |  | Ongoing
NIS2 conformiteit | Data Scientist | jun/26 | 0.4 | Demand |  |  |  | Ongoing
NIS2 conformiteit | Data Scientist | jul/26 | 0.4 | Demand |  |  |  | Ongoing
NIS2 conformiteit | Data Scientist | aug/26 | 0.4 | Demand |  |  |  | Ongoing
NIS2 conformiteit | Data Scientist | sep/26 | 0.4 | Demand |  |  |  | Ongoing
NIS2 conformiteit | Data Scientist | okt/26 | 0.4 | Demand |  |  |  | Ongoing
NIS2 conformiteit | Data Scientist | nov/26 | 0.4 | Demand |  |  |  | Ongoing
NIS2 conformiteit | Data Scientist | dec/26 | 0.4 | Demand |  |  |  | Ongoing
NIS2 conformiteit | Data Scientist | jan/27 | 0.4 | Demand |  |  |  | Ongoing
NIS2 conformiteit | Data Scientist | feb/27 | 0.4 | Demand |  |  |  | Ongoing
NIS2 conformiteit | Data Scientist | mrt/27 | 0.4 | Demand |  |  |  | Ongoing
NIS2 conformiteit | Business Analist | apr/26 | 0.5 | Demand |  |  |  | Ongoing
NIS2 conformiteit | Business Analist | mei/26 | 0.5 | Demand |  |  |  | Ongoing
NIS2 conformiteit | Business Analist | jun/26 | 0.5 | Demand |  |  |  | Ongoing
NIS2 conformiteit | Business Analist | jul/26 | 0.5 | Demand |  |  |  | Ongoing
NIS2 conformiteit | Business Analist | aug/26 | 0.5 | Demand |  |  |  | Ongoing
NIS2 conformiteit | Business Analist | sep/26 | 0.5 | Demand |  |  |  | Ongoing
NIS2 conformiteit | Business Analist | okt/26 | 0.5 | Demand |  |  |  | Ongoing
NIS2 conformiteit | Business Analist | nov/26 | 0.5 | Demand |  |  |  | Ongoing
NIS2 conformiteit | Business Analist | dec/26 | 0.5 | Demand |  |  |  | Ongoing
NIS2 conformiteit | Business Analist | jan/27 | 0.5 | Demand |  |  |  | Ongoing
NIS2 conformiteit | Business Analist | feb/27 | 0.5 | Demand |  |  |  | Ongoing
NIS2 conformiteit | Business Analist | mrt/27 | 0.5 | Demand |  |  |  | Ongoing
Procesoptimalisatie aankoop | Project Lead | apr/26 | 0.3 | Demand |  |  |  | Backlog
Procesoptimalisatie aankoop | Project Lead | mei/26 | 0.3 | Demand |  |  |  | Backlog
Procesoptimalisatie aankoop | Project Lead | jun/26 | 0.2 | Demand |  |  |  | Backlog
Procesoptimalisatie aankoop | Project Lead | jul/26 | 0.3 | Demand |  |  |  | Backlog
Procesoptimalisatie aankoop | Project Lead | aug/26 | 0.7 | Demand |  |  |  | Backlog
Procesoptimalisatie aankoop | Project Lead | sep/26 | 0.3 | Demand |  |  |  | Backlog
Procesoptimalisatie aankoop | Project Lead | okt/26 | 0.2 | Demand |  |  |  | Backlog
Procesoptimalisatie aankoop | Project Lead | nov/26 | 0.5 | Demand |  |  |  | Backlog
Procesoptimalisatie aankoop | Project Lead | dec/26 | 0.3 | Demand |  |  |  | Backlog
Procesoptimalisatie aankoop | Project Lead | jan/27 | 0.3 | Demand |  |  |  | Backlog
Procesoptimalisatie aankoop | Project Lead | feb/27 | 0.3 | Demand |  |  |  | Backlog
Procesoptimalisatie aankoop | Project Lead | mrt/27 | 0.4 | Demand |  |  |  | Backlog
Procesoptimalisatie aankoop | Product Owner | apr/26 | 0.4 | Demand |  |  |  | Backlog
Procesoptimalisatie aankoop | Product Owner | mei/26 | 0.4 | Demand |  |  |  | Backlog
Procesoptimalisatie aankoop | Product Owner | jun/26 | 0.4 | Demand |  |  |  | Backlog
Procesoptimalisatie aankoop | Product Owner | jul/26 | 0.4 | Demand |  |  |  | Backlog
Procesoptimalisatie aankoop | Product Owner | aug/26 | 0.4 | Demand |  |  |  | Backlog
Procesoptimalisatie aankoop | Product Owner | sep/26 | 0.4 | Demand |  |  |  | Backlog
Procesoptimalisatie aankoop | Product Owner | okt/26 | 0.4 | Demand |  |  |  | Backlog
Procesoptimalisatie aankoop | Product Owner | nov/26 | 0.4 | Demand |  |  |  | Backlog
Procesoptimalisatie aankoop | Product Owner | dec/26 | 0.4 | Demand |  |  |  | Backlog
Procesoptimalisatie aankoop | Product Owner | jan/27 | 0.4 | Demand |  |  |  | Backlog
Procesoptimalisatie aankoop | Product Owner | feb/27 | 0.4 | Demand |  |  |  | Backlog
Procesoptimalisatie aankoop | Product Owner | mrt/27 | 0.4 | Demand |  |  |  | Backlog
Procesoptimalisatie aankoop | Data Scientist | apr/26 | 0.5 | Demand |  |  |  | Backlog
Procesoptimalisatie aankoop | Data Scientist | mei/26 | 0.5 | Demand |  |  |  | Backlog
Procesoptimalisatie aankoop | Data Scientist | jun/26 | 0.5 | Demand |  |  |  | Backlog
Procesoptimalisatie aankoop | Data Scientist | jul/26 | 0.5 | Demand |  |  |  | Backlog
Procesoptimalisatie aankoop | Data Scientist | aug/26 | 0.5 | Demand |  |  |  | Backlog
Procesoptimalisatie aankoop | Data Scientist | sep/26 | 0.5 | Demand |  |  |  | Backlog
Procesoptimalisatie aankoop | Data Scientist | okt/26 | 0.5 | Demand |  |  |  | Backlog
Procesoptimalisatie aankoop | Data Scientist | nov/26 | 0.5 | Demand |  |  |  | Backlog
Procesoptimalisatie aankoop | Data Scientist | dec/26 | 0.5 | Demand |  |  |  | Backlog
Procesoptimalisatie aankoop | Data Scientist | jan/27 | 0.5 | Demand |  |  |  | Backlog
Procesoptimalisatie aankoop | Data Scientist | feb/27 | 0.5 | Demand |  |  |  | Backlog
Procesoptimalisatie aankoop | Data Scientist | mrt/27 | 0.5 | Demand |  |  |  | Backlog
Procesoptimalisatie aankoop | Business Analist | apr/26 | 0.7 | Demand |  |  |  | Backlog
Procesoptimalisatie aankoop | Business Analist | mei/26 | 0.7 | Demand |  |  |  | Backlog
Procesoptimalisatie aankoop | Business Analist | jun/26 | 0.3 | Demand |  |  |  | Backlog
Procesoptimalisatie aankoop | Business Analist | jul/26 | 0.7 | Demand |  |  |  | Backlog
Procesoptimalisatie aankoop | Business Analist | aug/26 | 0.7 | Demand |  |  |  | Backlog
Procesoptimalisatie aankoop | Business Analist | sep/26 | 0.7 | Demand |  |  |  | Backlog
Procesoptimalisatie aankoop | Business Analist | okt/26 | 0.7 | Demand |  |  |  | Backlog
Procesoptimalisatie aankoop | Business Analist | nov/26 | 0.7 | Demand |  |  |  | Backlog
Procesoptimalisatie aankoop | Business Analist | dec/26 | 0.3 | Demand |  |  |  | Backlog
Procesoptimalisatie aankoop | Business Analist | jan/27 | 0.7 | Demand |  |  |  | Backlog
Procesoptimalisatie aankoop | Business Analist | feb/27 | 0.7 | Demand |  |  |  | Backlog
Procesoptimalisatie aankoop | Business Analist | mrt/27 | 0.7 | Demand |  |  |  | Backlog
Procesoptimalisatie aankoop | DevOps Engineer | apr/26 | 0.7 | Demand |  |  |  | Backlog
Procesoptimalisatie aankoop | DevOps Engineer | mei/26 | 0.7 | Demand |  |  |  | Backlog
Procesoptimalisatie aankoop | DevOps Engineer | jun/26 | 0.7 | Demand |  |  |  | Backlog
Procesoptimalisatie aankoop | DevOps Engineer | jul/26 | 0.4 | Demand |  |  |  | Backlog
Procesoptimalisatie aankoop | DevOps Engineer | aug/26 | 0.4 | Demand |  |  |  | Backlog
Procesoptimalisatie aankoop | DevOps Engineer | sep/26 | 0.4 | Demand |  |  |  | Backlog
Procesoptimalisatie aankoop | DevOps Engineer | okt/26 | 0.3 | Demand |  |  |  | Backlog
Procesoptimalisatie aankoop | DevOps Engineer | nov/26 | 0.2 | Demand |  |  |  | Backlog
Procesoptimalisatie aankoop | DevOps Engineer | dec/26 | 0.5 | Demand |  |  |  | Backlog
Procesoptimalisatie aankoop | DevOps Engineer | jan/27 | 0.3 | Demand |  |  |  | Backlog
Procesoptimalisatie aankoop | DevOps Engineer | feb/27 | 0.3 | Demand |  |  |  | Backlog
Procesoptimalisatie aankoop | DevOps Engineer | mrt/27 | 0.3 | Demand |  |  |  | Backlog
| Software Architect | apr/26 | 0.3 | Supply | Jan De Smet | 5 | Kennisoverdracht!
| Software Architect | mei/26 | 0.5 | Supply | Jan De Smet | 5 | Kennisoverdracht!
| Software Architect | jun/26 | 0.6 | Supply | Jan De Smet | 5 | Kennisoverdracht!
| Software Architect | jul/26 | 1 | Supply | Jan De Smet | 5 | Kennisoverdracht!
| Software Architect | aug/26 | 0 | Supply | Jan De Smet | 5 | Kennisoverdracht!
| Software Architect | sep/26 | 0 | Supply | Jan De Smet | 5 | Kennisoverdracht!
| Software Architect | okt/26 | 0.4 | Supply | Jan De Smet | 5 | Kennisoverdracht!
| Software Architect | nov/26 | 0.5 | Supply | Jan De Smet | 5 | Kennisoverdracht!
| Software Architect | dec/26 | 0.6 | Supply | Jan De Smet | 5 | Kennisoverdracht!
| Software Architect | jan/27 | 0.7 | Supply | Jan De Smet | 5 | Kennisoverdracht!
| Software Architect | feb/27 | 0.8 | Supply | Jan De Smet | 5 | Kennisoverdracht!
| Software Architect | mrt/27 | 0.9 | Supply | Jan De Smet | 5 | Kennisoverdracht!
| Product Owner | apr/26 | 0.4 | Supply | An Verstraete | 2 | OK
| Product Owner | mei/26 | 0.4 | Supply | An Verstraete | 2 | OK
| Product Owner | jun/26 | 0.4 | Supply | An Verstraete | 2 | OK
| Product Owner | jul/26 | 1 | Supply | An Verstraete | 2 | OK
| Product Owner | aug/26 | 0.6 | Supply | An Verstraete | 2 | OK
| Product Owner | sep/26 | 0.4 | Supply | An Verstraete | 2 | OK
| Product Owner | okt/26 | 0.4 | Supply | An Verstraete | 2 | OK
| Product Owner | nov/26 | 0.4 | Supply | An Verstraete | 2 | OK
| Product Owner | dec/26 | 0.6 | Supply | An Verstraete | 2 | OK
| Product Owner | jan/27 | 0.4 | Supply | An Verstraete | 2 | OK
| Product Owner | feb/27 | 0.4 | Supply | An Verstraete | 2 | OK
| Product Owner | mrt/27 | 0.4 | Supply | An Verstraete | 2 | OK
| Project Lead | apr/26 | 0.6 | Supply | Sarah Willems | 4 | Back-up trainen
| Project Lead | mei/26 | 0.6 | Supply | Sarah Willems | 4 | Back-up trainen
| Project Lead | jun/26 | 0.6 | Supply | Sarah Willems | 4 | Back-up trainen
| Project Lead | jul/26 | 0.8 | Supply | Sarah Willems | 4 | Back-up trainen
| Project Lead | aug/26 | 0.7 | Supply | Sarah Willems | 4 | Back-up trainen
| Project Lead | sep/26 | 0.6 | Supply | Sarah Willems | 4 | Back-up trainen
| Project Lead | okt/26 | 0.6 | Supply | Sarah Willems | 4 | Back-up trainen
| Project Lead | nov/26 | 0.6 | Supply | Sarah Willems | 4 | Back-up trainen
| Project Lead | dec/26 | 0.3 | Supply | Sarah Willems | 4 | Back-up trainen
| Project Lead | jan/27 | 0.6 | Supply | Sarah Willems | 4 | Back-up trainen
| Project Lead | feb/27 | 0.6 | Supply | Sarah Willems | 4 | Back-up trainen
| Project Lead | mrt/27 | 0.6 | Supply | Sarah Willems | 4 | Back-up trainen
| DevOps Engineer | apr/26 | 0.3 | Supply | Koen Mertens | 2 | OK
| DevOps Engineer | mei/26 | 0.3 | Supply | Koen Mertens | 2 | OK
| DevOps Engineer | jun/26 | 0.3 | Supply | Koen Mertens | 2 | OK
| DevOps Engineer | jul/26 | 0.6 | Supply | Koen Mertens | 2 | OK
| DevOps Engineer | aug/26 | 0.5 | Supply | Koen Mertens | 2 | OK
| DevOps Engineer | sep/26 | 0.3 | Supply | Koen Mertens | 2 | OK
| DevOps Engineer | okt/26 | 0.3 | Supply | Koen Mertens | 2 | OK
| DevOps Engineer | nov/26 | 0.3 | Supply | Koen Mertens | 2 | OK
| DevOps Engineer | dec/26 | 0.6 | Supply | Koen Mertens | 2 | OK
| DevOps Engineer | jan/27 | 0.3 | Supply | Koen Mertens | 2 | OK
| DevOps Engineer | feb/27 | 0.3 | Supply | Koen Mertens | 2 | OK
| DevOps Engineer | mrt/27 | 0.3 | Supply | Koen Mertens | 2 | OK
| Business Analist | apr/26 | 0.9 | Supply | Sofie Peeters | 4 | Extra capaciteit nodig
| Business Analist | mei/26 | 0.9 | Supply | Sofie Peeters | 4 | Extra capaciteit nodig
| Business Analist | jun/26 | 0.9 | Supply | Sofie Peeters | 4 | Extra capaciteit nodig
| Business Analist | jul/26 | 0.7 | Supply | Sofie Peeters | 4 | Extra capaciteit nodig
| Business Analist | aug/26 | 0.6 | Supply | Sofie Peeters | 4 | Extra capaciteit nodig
| Business Analist | sep/26 | 0.9 | Supply | Sofie Peeters | 4 | Extra capaciteit nodig
| Business Analist | okt/26 | 0.9 | Supply | Sofie Peeters | 4 | Extra capaciteit nodig
| Business Analist | nov/26 | 0.9 | Supply | Sofie Peeters | 4 | Extra capaciteit nodig
| Business Analist | dec/26 | 0.4 | Supply | Sofie Peeters | 4 | Extra capaciteit nodig
| Business Analist | jan/27 | 0.9 | Supply | Sofie Peeters | 4 | Extra capaciteit nodig
| Business Analist | feb/27 | 0.9 | Supply | Sofie Peeters | 4 | Extra capaciteit nodig
| Business Analist | mrt/27 | 0.9 | Supply | Sofie Peeters | 4 | Extra capaciteit nodig
| Project Lead | apr/26 | 0.8 | Supply | Tom Peeters | 5 | Kritiek risico!
| Project Lead | mei/26 | 0.8 | Supply | Tom Peeters | 5 | Kritiek risico!
| Project Lead | jun/26 | 0.8 | Supply | Tom Peeters | 5 | Kritiek risico!
| Project Lead | jul/26 | 0.5 | Supply | Tom Peeters | 5 | Kritiek risico!
| Project Lead | aug/26 | 0.4 | Supply | Tom Peeters | 5 | Kritiek risico!
| Project Lead | sep/26 | 0.8 | Supply | Tom Peeters | 5 | Kritiek risico!
| Project Lead | okt/26 | 0.8 | Supply | Tom Peeters | 5 | Kritiek risico!
| Project Lead | nov/26 | 0.8 | Supply | Tom Peeters | 5 | Kritiek risico!
| Project Lead | dec/26 | 0.5 | Supply | Tom Peeters | 5 | Kritiek risico!
| Project Lead | jan/27 | 0.8 | Supply | Tom Peeters | 5 | Kritiek risico!
| Project Lead | feb/27 | 0.8 | Supply | Tom Peeters | 5 | Kritiek risico!
| Project Lead | mrt/27 | 0.8 | Supply | Tom Peeters | 5 | Kritiek risico!
| Software Architect | apr/26 | 0.7 | Supply | Sam Pieters | 3 | Monitoren
| Software Architect | mei/26 | 0.7 | Supply | Sam Pieters | 3 | Monitoren
| Software Architect | jun/26 | 0.7 | Supply | Sam Pieters | 3 | Monitoren
| Software Architect | jul/26 | 0.6 | Supply | Sam Pieters | 3 | Monitoren
| Software Architect | aug/26 | 0.6 | Supply | Sam Pieters | 3 | Monitoren
| Software Architect | sep/26 | 0.7 | Supply | Sam Pieters | 3 | Monitoren
| Software Architect | okt/26 | 0.7 | Supply | Sam Pieters | 3 | Monitoren
| Software Architect | nov/26 | 0.7 | Supply | Sam Pieters | 3 | Monitoren
| Software Architect | dec/26 | 0.3 | Supply | Sam Pieters | 3 | Monitoren
| Software Architect | jan/27 | 0.7 | Supply | Sam Pieters | 3 | Monitoren
| Software Architect | feb/27 | 0.7 | Supply | Sam Pieters | 3 | Monitoren
| Software Architect | mrt/27 | 0.7 | Supply | Sam Pieters | 3 | Monitoren

## 5. Dashboard
SPOF resource dashboard
Sum of FTE | Column Labels
Row Labels | Demand | Supply | Grand Total
apr/26 | 5.1 | 4 | 9.1
aug/26 | 4.4 | 3.4 | 7.8
dec/26 | 4.1 | 3.3 | 7.4
feb/27 | 4.7 | 4.5 | 9.2
jan/27 | 4.7 | 4.4 | 9.1
jul/26 | 4 | 5.2 | 9.2
jun/26 | 4.6 | 4.3 | 8.9
mei/26 | 5.1 | 4.2 | 9.3
mrt/27 | 4.8 | 4.6 | 9.4
nov/26 | 4.8 | 4.2 | 9
okt/26 | 4.6 | 4.1 | 8.7
sep/26 | 4.8 | 3.7 | 8.5
Grand Total | 55.7 | 49.9 | 105.6
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.